## Sheet1
Chef POC Estimation
S.No. |  | Action | Owner | Start Date | End Date | Status | Est. Efforts | Remarks
| Installation | Require VMs for chef | Tusar IT | 2017-09-22 | 2017-09-26 | In-progress |  | Waiting for VMs from IT Team, followed up multiple times
|  | Set chef-workstation | Saurabh | 2017-09-27 | 2017-09-27 | Not started | 3hrs
|  | Installation of Chef-server on new Linux Machine | Saurabh | 2017-09-27 | 2017-09-27 | Not started | 2 hr
|  | Bootstrap Windows chef-client | Saurabh | 2017-09-27 | 2017-09-27 | Not started | 1hr
|  | Verify connectivity between chef-server and chef-client | Saurabh | 2017-09-27 | 2017-09-27 | Not started | 1hr
Cookbook Upload on Server
|  | Implementation of Java Cookbook | Saurabh | 2017-09-28 | 2017-09-28 | Not started
|  | Implementation of Git Cookbook | Saurabh | 2017-09-29 | 2017-09-29 | Not started
|  | Implementation of TFS CookBook | Saurabh | 2017-10-03 | 2017-10-04 | Not started
|  | Implementation of Visual Studio CookBook | Saurabh | 2017-10-05 | 2017-10-06 | Not started
CooBook installed on client
|  | Implementation of Java Cookbook | Saurabh | 2017-10-06 | 2017-10-06 | Not started
|  | Implementation of Git Cookbook | Saurabh | 2017-10-06 | 2017-10-06 | Not started
|  | Implementation of TFS CookBook | Saurabh | 2017-10-10 | 2017-10-11 | Not started |  | These are the tentative dates as I haven't worked on TFS and Visual studio set up
|  | Implementation of Visual Studio CookBook | Saurabh | 2017-10-12 | 2017-10-13 | Not started
| Test-Kitchen | [6 empty] | Test kitchen will be implemented we receive above plan sign off
|  | SetUp of test-kitchen | [5 empty] | I will input the date as per completion of about set up
Test case for Java Cookbook
Test case for Git Cookbook
Test case for TFS CookBook
Test case for Visual Studio CookBook